## Backlog
ID | Type | Summary | Parent Epic | Priority | Story Points | Sprint | Status
EPIC-1 | Epic | Backend Infrastructure |  | Highest | 26 | Sprint 1 & 4 | To Do
US-36 | Story | Database schema design and Prisma migrations | Backend Infrastructure | High | 6 | Sprint 1 | To Do
| Task | Design Prisma schema (10 models, relations, indexes) | Backend Infrastructure |  |  | Sprint 1 | To Do
| Task | Write seed script (admin user + default settings) | Backend Infrastructure |  |  | Sprint 1 | To Do
| Task | Run initial migration on dev DB | Backend Infrastructure |  |  | Sprint 1 | To Do
US-37 | Story | REST API scaffold with auth middleware | Backend Infrastructure | High | 8 | Sprint 1 | To Do
| Task | Setup Fastify with route structure and plugins | Backend Infrastructure |  |  | Sprint 1 | To Do
| Task | Implement JWT auth middleware (access + refresh) | Backend Infrastructure |  |  | Sprint 1 | To Do
| Task | Add role-based access control (public/user/admin) | Backend Infrastructure |  |  | Sprint 1 | To Do
| Task | Add Zod request validation and error handling | Backend Infrastructure |  |  | Sprint 1 | To Do
| Task | Configure CORS and rate limiting | Backend Infrastructure |  |  | Sprint 1 | To Do
US-38 | Story | File storage setup with Cloudflare R2 | Backend Infrastructure | High | 4 | Sprint 1 | To Do
| Task | Configure S3 client for R2 bucket | Backend Infrastructure |  |  | Sprint 1 | To Do
| Task | Implement Multer upload middleware (size/type validation) | Backend Infrastructure |  |  | Sprint 1 | To Do
| Task | Create upload + delete utility functions | Backend Infrastructure |  |  | Sprint 1 | To Do
US-39 | Story | Cron jobs for flash sales and voucher expiry | Backend Infrastructure | High | 4 | Sprint 4 | To Do
| Task | Implement flash sale cron (every minute, activate/deactivate) | Backend Infrastructure |  |  | Sprint 4 | To Do
| Task | Implement voucher expiry cron (every hour) | Backend Infrastructure |  |  | Sprint 4 | To Do
| Task | Add logging and error handling for jobs | Backend Infrastructure |  |  | Sprint 4 | To Do
US-40 | Story | CI/CD pipeline with GitHub Actions | Backend Infrastructure | Medium | 4 | Sprint 5 | To Do
| Task | Create GitHub Actions workflow (lint, build, deploy) | Backend Infrastructure |  |  | Sprint 5 | To Do
| Task | Configure Vercel auto-deploy for frontend | Backend Infrastructure |  |  | Sprint 5 | To Do
| Task | Configure Railway/Docker deploy for backend | Backend Infrastructure |  |  | Sprint 5 | To Do
EPIC-2 | Epic | Public Website |  | Highest | 50 | Sprint 1 & 2 | To Do
US-01 | Story | Hero section with cover video and brand identity | Public Website | High | 3 | Sprint 1 | To Do
| Task | Full-screen video background with Ken Burns fallback | Public Website |  |  | Sprint 1 | To Do
| Task | GSAP staggered text entrance animation | Public Website |  |  | Sprint 1 | To Do
| Task | Animated wave SVG separator + scroll chevron | Public Website |  |  | Sprint 1 | To Do
US-02 | Story | About section with business story and features | Public Website | Medium | 3 | Sprint 1 | To Do
| Task | Split layout: text + parallax image | Public Website |  |  | Sprint 1 | To Do
| Task | 2x2 feature cards with GSAP scroll entrance | Public Website |  |  | Sprint 1 | To Do
US-03 | Story | Photo gallery with masonry grid and lightbox | Public Website | High | 5 | Sprint 1 | To Do
| Task | CSS columns masonry layout (responsive) | Public Website |  |  | Sprint 1 | To Do
| Task | GSAP clip-path reveal animation on scroll | Public Website |  |  | Sprint 1 | To Do
| Task | Lightbox modal with prev/next + keyboard nav | Public Website |  |  | Sprint 1 | To Do
| Task | Fetch images from API (gallery section) | Public Website |  |  | Sprint 1 | To Do
US-04 | Story | Menu page with Standard and Extra versions | Public Website | High | 5 | Sprint 1 | To Do
| Task | Standard / Extra toggle or tab component | Public Website |  |  | Sprint 1 | To Do
| Task | Menu item cards (name, desc, price, image) | Public Website |  |  | Sprint 1 | To Do
| Task | Fetch from /api/menu endpoint | Public Website |  |  | Sprint 1 | To Do
US-05 | Story | Emplacements showcase (cabanes, mer, plage) | Public Website | High | 5 | Sprint 1 | To Do
| Task | Emplacement cards with image, desc, price, capacity | Public Website |  |  | Sprint 1 | To Do
| Task | Horizontal scroll on desktop, vertical on mobile | Public Website |  |  | Sprint 1 | To Do
| Task | 3D tilt hover effect | Public Website |  |  | Sprint 1 | To Do
US-06 | Story | Active vouchers display on website | Public Website | Medium | 3 | Sprint 2 | To Do
| Task | Voucher cards (code, discount, expiry) | Public Website |  |  | Sprint 2 | To Do
| Task | Fetch from /api/vouchers/active | Public Website |  |  | Sprint 2 | To Do
US-07 | Story | Flash sale section with countdown timer | Public Website | High | 5 | Sprint 4 | To Do
| Task | Countdown timer component (days/hours/min/sec) | Public Website |  |  | Sprint 4 | To Do
| Task | Client-side calculation from ends_at timestamp | Public Website |  |  | Sprint 4 | To Do
| Task | Auto-hide when expired | Public Website |  |  | Sprint 4 | To Do
US-08 | Story | Approved customer reviews display | Public Website | Medium | 3 | Sprint 2 | To Do
| Task | Star rating display component | Public Website |  |  | Sprint 2 | To Do
| Task | Review cards (rating, comment, user, date) | Public Website |  |  | Sprint 2 | To Do
| Task | Carousel or grid layout | Public Website |  |  | Sprint 2 | To Do
US-09 | Story | Social media redirect buttons (WA/IG/Messenger) | Public Website | High | 2 | Sprint 1 | To Do
| Task | WhatsApp wa.me link, Instagram profile link, Messenger m.me link | Public Website |  |  | Sprint 1 | To Do
| Task | Floating action buttons on mobile | Public Website |  |  | Sprint 1 | To Do
US-10 | Story | Location section with Google Maps | Public Website | Medium | 3 | Sprint 1 | To Do
| Task | Google Maps iframe embed from config lat/lng | Public Website |  |  | Sprint 1 | To Do
| Task | Contact info cards (address, phone, hours) | Public Website |  |  | Sprint 1 | To Do
| Task | Get directions link | Public Website |  |  | Sprint 1 | To Do
US-11 | Story | Multi-language support FR/AR/EN | Public Website | High | 8 | Sprint 1 | To Do
| Task | Vue I18n setup with 3 JSON locale files | Public Website |  |  | Sprint 1 | To Do
| Task | Language switcher in header | Public Website |  |  | Sprint 1 | To Do
| Task | Arabic RTL layout support (Tailwind rtl:) | Public Website |  |  | Sprint 1 | To Do
| Task | Persist language preference in localStorage | Public Website |  |  | Sprint 1 | To Do
US-12 | Story | Responsive design for all screen sizes | Public Website | High | 8 | Sprint 5 | To Do
| Task | Desktop (1920px), tablet (768px), mobile (375px) pass | Public Website |  |  | Sprint 5 | To Do
| Task | Mobile hamburger menu with smooth animation | Public Website |  |  | Sprint 5 | To Do
| Task | Touch-friendly interactions | Public Website |  |  | Sprint 5 | To Do
| Task | Cross-browser testing (Chrome, Firefox, Safari) | Public Website |  |  | Sprint 5 | To Do
EPIC-3 | Epic | User Authentication |  | Highest | 17 | Sprint 2 | To Do
US-13 | Story | User registration with email or phone + password | User Authentication | High | 5 | Sprint 2 | To Do
| Task | POST /api/auth/register endpoint | User Authentication |  |  | Sprint 2 | To Do
| Task | Zod validation + bcrypt hashing (12 rounds) | User Authentication |  |  | Sprint 2 | To Do
| Task | Duplicate email/phone check | User Authentication |  |  | Sprint 2 | To Do
| Task | Return JWT access + refresh tokens | User Authentication |  |  | Sprint 2 | To Do
| Task | Registration form component | User Authentication |  |  | Sprint 2 | To Do
US-14 | Story | User login with JWT tokens | User Authentication | High | 3 | Sprint 2 | To Do
| Task | POST /api/auth/login endpoint | User Authentication |  |  | Sprint 2 | To Do
| Task | Access token (15min) + refresh token (7d httpOnly cookie) | User Authentication |  |  | Sprint 2 | To Do
| Task | Auto-refresh interceptor in frontend API client | User Authentication |  |  | Sprint 2 | To Do
US-15 | Story | Google and Facebook OAuth login | User Authentication | Medium | 5 | Sprint 2 | To Do
| Task | Passport.js Google strategy + callback | User Authentication |  |  | Sprint 2 | To Do
| Task | Passport.js Facebook strategy + callback | User Authentication |  |  | Sprint 2 | To Do
| Task | Create or link user account on OAuth callback | User Authentication |  |  | Sprint 2 | To Do
| Task | Social login buttons in frontend | User Authentication |  |  | Sprint 2 | To Do
US-16 | Story | Password reset via email | User Authentication | High | 4 | Sprint 2 | To Do
| Task | POST /api/auth/forgot-password (send reset link) | User Authentication |  |  | Sprint 2 | To Do
| Task | Reset token with 1h expiry in DB | User Authentication |  |  | Sprint 2 | To Do
| Task | POST /api/auth/reset-password (validate + update) | User Authentication |  |  | Sprint 2 | To Do
EPIC-4 | Epic | Reservation System |  | Highest | 11 | Sprint 2 & 4 | To Do
US-17 | Story | Reservation form with WhatsApp send | Reservation System | High | 5 | Sprint 2 | To Do
| Task | Form: name, phone, date, guests, message, voucher code | Reservation System |  |  | Sprint 2 | To Do
| Task | Validation with shake animation on errors | Reservation System |  |  | Sprint 2 | To Do
| Task | Build WhatsApp message + open wa.me URL | Reservation System |  |  | Sprint 2 | To Do
| Task | Save reservation to DB via POST /api/reservations | Reservation System |  |  | Sprint 2 | To Do
US-18 | Story | Apply voucher code to reservation | Reservation System | Medium | 4 | Sprint 4 | To Do
| Task | POST /api/vouchers/validate endpoint | Reservation System |  |  | Sprint 4 | To Do
| Task | Check: exists, active, not expired, uses < max | Reservation System |  |  | Sprint 4 | To Do
| Task | Display discount in form before sending | Reservation System |  |  | Sprint 4 | To Do
US-19 | Story | View reservation history (logged-in user) | Reservation System | Low | 3 | Sprint 4 | To Do
| Task | GET /api/reservations/mine endpoint (authenticated) | Reservation System |  |  | Sprint 4 | To Do
| Task | Simple list view in user profile page | Reservation System |  |  | Sprint 4 | To Do
EPIC-5 | Epic | Reviews & Feedback |  | High | 6 | Sprint 2 | To Do
US-20 | Story | Submit a review as logged-in user | Reviews & Feedback | High | 5 | Sprint 2 | To Do
| Task | POST /api/reviews endpoint (authenticated) | Reviews & Feedback |  |  | Sprint 2 | To Do
| Task | Star rating component (1-5 clickable) | Reviews & Feedback |  |  | Sprint 2 | To Do
| Task | Comment text area | Reviews & Feedback |  |  | Sprint 2 | To Do
| Task | Saved with is_approved=false by default | Reviews & Feedback |  |  | Sprint 2 | To Do
US-21 | Story | Display only admin-approved reviews | Reviews & Feedback | High | 2 | Sprint 2 | To Do
| Task | GET /api/reviews (WHERE is_approved AND is_visible) | Reviews & Feedback |  |  | Sprint 2 | To Do
| Task | Frontend review card component | Reviews & Feedback |  |  | Sprint 2 | To Do
EPIC-6 | Epic | Backoffice - Content Management |  | Highest | 30 | Sprint 3 | To Do
US-22 | Story | Admin secure login to backoffice | Backoffice - Content Management | High | 4 | Sprint 3 | To Do
| Task | Admin login page at /admin/login | Backoffice - Content Management |  |  | Sprint 3 | To Do
| Task | Role check middleware (req.user.role === admin) | Backoffice - Content Management |  |  | Sprint 3 | To Do
| Task | Redirect to login if not authenticated | Backoffice - Content Management |  |  | Sprint 3 | To Do
US-23 | Story | Admin menu management CRUD | Backoffice - Content Management | High | 8 | Sprint 3 | To Do
| Task | CRUD endpoints for menu categories | Backoffice - Content Management |  |  | Sprint 3 | To Do
| Task | CRUD endpoints for menu items | Backoffice - Content Management |  |  | Sprint 3 | To Do
| Task | Form: name (FR/EN/AR), desc, price_standard, price_extra, image | Backoffice - Content Management |  |  | Sprint 3 | To Do
| Task | Drag-to-reorder with sort_order update | Backoffice - Content Management |  |  | Sprint 3 | To Do
| Task | is_available toggle per item | Backoffice - Content Management |  |  | Sprint 3 | To Do
US-24 | Story | Admin image management for all sections | Backoffice - Content Management | High | 8 | Sprint 3 | To Do
| Task | Upload to R2 via /api/admin/images | Backoffice - Content Management |  |  | Sprint 3 | To Do
| Task | Section selector (hero, gallery, menu, emplacement) | Backoffice - Content Management |  |  | Sprint 3 | To Do
| Task | Grid view with drag-to-reorder | Backoffice - Content Management |  |  | Sprint 3 | To Do
| Task | Delete with confirmation dialog | Backoffice - Content Management |  |  | Sprint 3 | To Do
US-25 | Story | Admin hero video and cover content editor | Backoffice - Content Management | Medium | 3 | Sprint 3 | To Do
| Task | Video upload to R2 | Backoffice - Content Management |  |  | Sprint 3 | To Do
| Task | Edit overlay text via site_settings | Backoffice - Content Management |  |  | Sprint 3 | To Do
US-26 | Story | Admin emplacement management | Backoffice - Content Management | High | 5 | Sprint 3 | To Do
| Task | CRUD for emplacements table | Backoffice - Content Management |  |  | Sprint 3 | To Do
| Task | Trilingual text fields + image upload | Backoffice - Content Management |  |  | Sprint 3 | To Do
| Task | Sort order management | Backoffice - Content Management |  |  | Sprint 3 | To Do
US-27 | Story | Admin site settings and SEO editor | Backoffice - Content Management | Medium | 4 | Sprint 3 | To Do
| Task | Key-value editor for site_settings table | Backoffice - Content Management |  |  | Sprint 3 | To Do
| Task | Fields: phone, email, address, about text, SEO keywords | Backoffice - Content Management |  |  | Sprint 3 | To Do
| Task | Changes reflect immediately on public site | Backoffice - Content Management |  |  | Sprint 3 | To Do
EPIC-7 | Epic | Backoffice - Vouchers & Flash Sales |  | High | 18 | Sprint 4 | To Do
US-28 | Story | Admin create and manage vouchers | Backoffice - Vouchers & Flash Sales | High | 6 | Sprint 4 | To Do
| Task | CRUD endpoints /api/admin/vouchers | Backoffice - Vouchers & Flash Sales |  |  | Sprint 4 | To Do
| Task | Form: code, discount_%, discount_amount, valid_from/until, max_uses | Backoffice - Vouchers & Flash Sales |  |  | Sprint 4 | To Do
| Task | Table view with status indicator | Backoffice - Vouchers & Flash Sales |  |  | Sprint 4 | To Do
| Task | Auto-generate code option | Backoffice - Vouchers & Flash Sales |  |  | Sprint 4 | To Do
US-29 | Story | Admin activate/deactivate vouchers | Backoffice - Vouchers & Flash Sales | High | 2 | Sprint 4 | To Do
| Task | Toggle endpoint PUT /api/admin/vouchers/:id/toggle | Backoffice - Vouchers & Flash Sales |  |  | Sprint 4 | To Do
| Task | Toggle button in voucher list UI | Backoffice - Vouchers & Flash Sales |  |  | Sprint 4 | To Do
US-30 | Story | Admin schedule flash sales | Backoffice - Vouchers & Flash Sales | High | 6 | Sprint 4 | To Do
| Task | CRUD endpoints /api/admin/flash-sales | Backoffice - Vouchers & Flash Sales |  |  | Sprint 4 | To Do
| Task | Form: title (3 langs), desc, discount_%, start/end datetime pickers, image | Backoffice - Vouchers & Flash Sales |  |  | Sprint 4 | To Do
| Task | Preview countdown timer in admin | Backoffice - Vouchers & Flash Sales |  |  | Sprint 4 | To Do
US-31 | Story | Auto-activate/deactivate flash sales (cron) | Backoffice - Vouchers & Flash Sales | High | 4 | Sprint 4 | To Do
| Task | node-cron every minute: activate where starts_at <= NOW() | Backoffice - Vouchers & Flash Sales |  |  | Sprint 4 | To Do
| Task | node-cron every minute: deactivate where ends_at <= NOW() | Backoffice - Vouchers & Flash Sales |  |  | Sprint 4 | To Do
| Task | Logging for job execution | Backoffice - Vouchers & Flash Sales |  |  | Sprint 4 | To Do
EPIC-8 | Epic | Backoffice - Moderation |  | High | 11 | Sprint 4 & 5 | To Do
US-32 | Story | Admin view all submitted reviews | Backoffice - Moderation | High | 3 | Sprint 4 | To Do
| Task | GET /api/admin/reviews (returns ALL reviews) | Backoffice - Moderation |  |  | Sprint 4 | To Do
| Task | Table: user, rating, comment, date, status | Backoffice - Moderation |  |  | Sprint 4 | To Do
US-33 | Story | Admin approve/reject/hide reviews | Backoffice - Moderation | High | 3 | Sprint 4 | To Do
| Task | PUT /api/admin/reviews/:id (approve/reject/hide) | Backoffice - Moderation |  |  | Sprint 4 | To Do
| Task | Action buttons per review row | Backoffice - Moderation |  |  | Sprint 4 | To Do
| Task | Bulk action support | Backoffice - Moderation |  |  | Sprint 4 | To Do
US-34 | Story | Admin view incoming reservations | Backoffice - Moderation | Medium | 3 | Sprint 4 | To Do
| Task | GET /api/admin/reservations | Backoffice - Moderation |  |  | Sprint 4 | To Do
| Task | Table with filters (date range, status) | Backoffice - Moderation |  |  | Sprint 4 | To Do
| Task | Click to view full details | Backoffice - Moderation |  |  | Sprint 4 | To Do
US-35 | Story | Admin view registered users | Backoffice - Moderation | Low | 2 | Sprint 5 | To Do
| Task | GET /api/admin/users | Backoffice - Moderation |  |  | Sprint 5 | To Do
| Task | Table: name, email/phone, provider, date | Backoffice - Moderation |  |  | Sprint 5 | To Do
| Task | Search and filter (read-only, no edit/delete) | Backoffice - Moderation |  |  | Sprint 5 | To Do

## Summary
Epic | Stories | Tasks | Story Points | Sprint | Priority
Backend Infrastructure | 5 | 17 | 26 | Sprint 1 & 4 | Highest
Public Website | 12 | 36 | 50 | Sprint 1 & 2 | Highest
User Authentication | 4 | 15 | 17 | Sprint 2 | Highest
Reservation System | 3 | 9 | 11 | Sprint 2 & 4 | Highest
Reviews & Feedback | 2 | 6 | 6 | Sprint 2 | High
Backoffice - Content Management | 6 | 20 | 30 | Sprint 3 | Highest
Backoffice - Vouchers & Flash Sales | 4 | 12 | 18 | Sprint 4 | High
Backoffice - Moderation | 4 | 11 | 11 | Sprint 4 & 5 | High
TOTAL | 40 | 126 | 169 | 5 Sprints